## Sequence of Execution
TaskID | Task | Execution | Estimated Time | Dependency | Comments
1.0 | Pre- Implementation Steps -Mention all the steps that are required to be executed as pre-requisite checks for the change
1.0.1 | Take the export of the below jobs
oj_Load_RPT_CUSTOMER_SCM_IHC
oj_Load_Master_RPT_Talent_Pos_Wkly_Snap_and_AAA_Objects
zz_oj_Load_RPT_CUSTOMER_SCM_IHC
2.0 | Sequence of Execution
2.0.1 | Matillion
| Fetch and checkout the latest master branch in AAW | Matillion Admins | 5 mins
2.0.2 | Snowflake
1 | Grant access to aaw_matillion_app_role for the below 2 dynamic tables 1. AAW.AER_BI_EDW.TAB_CUSTOMER_SCM_IHC_COMPANY_DT 2. AAW.ACT_BI_EDW.TAB_CUSTOMER_SCM_IHC_DT
2 | inserting rows in the control table . Execute the below scripts
snowflake/aaw/aaw-elt/dml_scripts/DS_S-531456_Scripts.sql
3.0 | Post-migration Validation
3.0.1 | Validate the changes in all the above jobs.
4.0 | BackOut Plan
4.0.1 | Revert the matillion changes using the job export | Matillion Admins | 10 mins
5.0 | Monitoring
Monitor the jobs in their upcoming schedules.
Note | If at any point the job / script fails - the admins need to send a mail to the requestor / TSM stating the same. Based on the situation the requesters might come in with a updated migration document via a mail with change manager and requestor TSM's in loop- and it will be executed. They can also choose to remigrate pending changes as part of a seperate CO.
At the end of migration Admins will send a mail stating the migration is completed
Note to Req | If at any step the requestor needs to be notified - we need a explit step in the sequence of execution. If mentioned a notification will be sent in teams channel
Matillion project and Environment variables will be taken a backup by default. Any backup of snowflake objects needs to be mentioned explicitly - Pre migration step or execution.
Backout plan will be executed post migration if the requester sends in a mail with change manager and requestor TSM's in loop
If there are dependencies within stories - it needs to be mentioned explicitly in the CO mail or needs to be clubbed in a single migration document (Prefereable)

## Matillion_Snowflake (hidden)
TaskID | Task | Execution | Estimated Time | Comments
1.0 | Pre- Implementation Steps -Mention all the steps that are required to be executed as pre-requisite checks for the change
NA
2.0 | Pre-Validation Steps -Mention all the validations that are required before change can be executed
2.0.1
3.0 | Import Object Metadata File Name - in BitBucket, Allegis Enterprise Data /<Rest Path>
3.0.1 | Snowflake
10 mins
3.0.2 | Matillion
| fetch and checkout in DCJ:- tj_Load_Absolute_Device_details;tj_Load_Absolute_Device_details_hist |  | 10 mins
3.0.3 | Qlik
na
4.0.1 | Export Object Metadata File Name
4.0.1.1 | na
5.0.1 | Import Object Metadata File Name
5.0.1.1 | na
6.0.1 | New Projects/Folders to Create
6.0.1.1 | na
7.0.1 | New Connections
7.0.1.1 | na
8.0.1 | Param Files
8.0.1.1 | na
9.0 | Scheduling considerations - Fill in if a schedule is to be turned on/off (otherwise state none)
9.0.1 | Mention the jobs and the full new schedule of them JOBS:_zz_oj_Load_RPT_Talent_Pos_Wkly_Snap_S451959 schedule the job for every 1 hr for next two days( thrusday and Friday)
10.0 | Deployment Steps- Indicate all the steps necessary for the change in sequencial manner for all applications (Snowflake, Qlik, Matillion)
10.0.1 | fetch and checkout the jobs in prod
11.0 | Post-Validation | POC from DA Team
11.0.1 | Indicate validation steps: Check to ensure Deployment Group has correct # of objects, data validation in Target tables, etc…
| check all the target table | Swarna
12.0 | BackOut Plan
12.0.1 | revert back all canges on view
12.0.2
12.0.3
13.0 | Monitoring
13.0.1 | Mention the jobs /Data replication tasks etc. that should require monitoring . Note: If Schedule Changes are mentioned, this section should have the jobnames whose schedules are being changed. | swarna

## Escalation Path - Dev check
Deployment Escalation | Software | Requestor |  | Admin Role |  | Data services Team
|  | Offshore | Onshore | Offshore | Onshore | Offshore | Onshore
| Matillion | Komal/Harshtha | Navitha | Srinivasulu Jadani |  | Naveen/ Deepak | Harika/ Barbara
Validation | Dev | QA | Additional Team members
| Komal/Harshitha |  | Navitha
Matillion
Environment variable
Schedules
OTL runs if required
Jobs migrated should be mentioned
Approximate Job run time in prod needs to be mentioned
New connections if present needs to be mentioned
Any S3 or Lambda changes needs to be mentioned
Snowflake | Qlik replicate steps if required
For any snowflake script, need to mention the role name and warehouse name to be used
Approximate script run times in prod needs to be mentioned

## Prod-Chg. Readiness Checklist
Production Change Readiness Checklist
Name of the Prod Change
# | Category | Question | Response Guidance (Mention NA if any question is not applicable for the change. If a whole category is not applicable - mention NA for all with a brief explanation for the entire category) | Supporting Documentation Link | Director Approval (Y/N) | Comments
1 | General
1.1 | IS Team(s) | What team(s) is requesting this deployment? | Data Services
1.2 | Overall Prod Change Schedule | What is the requested deployment schedule (date and time ranges)? | 22th Jan 2026, 5:30 AM EST
1.3 | Overall Change Duration | What is the expected duration of the deployment? | 30 mins
1.4 | Change Type | What is being deployed? (Data/Code, Both)? | Matillion Job
1.5 | Matillion Coding Standard | Does your change involve Matillion Code ? If Yes, are there any job varibales in your code that has environmental details (like server IPs, User Passwords, URLs etc)? | Yes,No
1.6 | Matillion Coding Standard | If Answered Yes to enviromental details in job variables, have you coordinated with DS Admins already to add the additional endpoint tracked for future change notifications? | NA
1.7 | Matillion Configuration | Does your change have any active Matillion endpoints /Source Systems/Target Systems? | NA
1.8 | Change Description & Justification | Deployment description along with business justification | Replace existing table RPT_CUSTOMER_SCM_IHC_VW with two new tables for Actalent and Aerotek in oj_Load_RPT_CUSTOMER_SCM_IHC job
1.9 | Impact | Does this deployment requires system downtime? | No
2 | Deployment Rigor
2.1 |  | Is this a first time deployment? | No
2.2 |  | Is the deployment high-risk ? | No
2.3 |  | Will the deployment affect a large group of people ? | NO
2.4 |  | Does the deployment impact a particularily high value area ? | NO
2.5 |  | Will this change have any impact on downstream systems ? | NO
3 | Pre-deployment Testing
3.1 | Perf Test POC | Who was the primary Performance tester? | Komal & Navitha
3.2 | Perf Testing vs Prod real load comparison and Test Results - Incremental | LOAD: How close to true production scenarios and traffic volumes were tested ? Please provide tested data volume and expected production data volume for Incremental load.
3.3 | Perf Testing vs Prod real load comparison and Test Results - One time load | In case of OTL - Please provide tested data volume and expected production data volume
3.4 | UAT/Functional testing | Functional /UAT : What was tested and what were the results? | Replaced existing table RPT_CUSTOMER_SCM_IHC_VW with two new tables for Actalent and Aerotek in oj_Load_RPT_CUSTOMER_SCM_IHC job and test the job by running in dev and pre prod environment
3.5 | Perf test reviewer | LOAD: Who approved the load test results?
3.6 | UAT/Business signoff POC | UAT: Who outside of IS performed UAT if done?
4 | Deployment Steps
4.1 |  | Are all deployment tasks listed? | Yes
4.2 |  | Are tasks at a detailed enough level? | Yes
4.3 |  | Is there a single, named owner on each deployment task? | Yes
4.4 |  | Do you have an identified escalation path for each major component of the deployment? | Can be defaulted to an answer
4.5 |  | How will the steps of the deployment process be communicated for "active" (e.g. deployment team) and "passive" (e.g. those who need to stay informed) team members. | Microsoft Teams' chat for Active Members collaborting about the change and/or Email Communication to the Passive Members
5 | Deployment Verification
5.1 |  | Is there a clear "definition of done" for the deployment? | Yes
5.2 |  | Is the criteria for a successfully deployment defined? | NA
5.3 |  | Named resources within IS listed that are responsible for verifying if the deployment is successful? | Komal & Navitha
5.4 |  | Named resources outside of IS listed that are responsible for verifying if the deployment is successful? | NA
6 | Monitoring and Alerting
6.1 | Post Deployment monitoring | What related systems require monitoring post-deployment? | Matillion
6.2 |  | How will all related systems be monitored after deployment to ensure the application is performing as expected? | NA
6.3 |  | What are the Run times/frequency/expected volume of records/any SLAs in production | 10 Mins approx.
7 | Rollback
7.1 |  | Is there a detailed, robust rollback plan? | Yes
7.2 |  | Has the rollback plan been executed in a non-PROD environment? | Yes
8 | Communication
7.1 | Communication POC | Who communicated the deployment details? | Data Services
7.2 | Notification contact points | Who/what teams need to be aware of this deployment? | Data Services , DA
7.3 | Communication Mode | Have all appropriate people and teams been made aware of this deployment? | Yes

## Prod-Chg. Readiness Checkli (2) (hidden)
Production Change Readiness Checklist
# | Category | Question | Response Guidance (Mention NA if any question is not applicable for the change. If a whole category is not applicable - mention NA for all with a brief explanation for the entire category) | Supporting Documentation Link | Director Approval (Y/N) | Comments
1 | General
1.1 | IS Team(s) | What team(s) is requesting this deployment? | Data Analytics
1.2 | Overall Prod Change Schedule | What is the requested deployment schedule (date and time ranges)? | 28/10/2024 5:00AM EST
1.3 | Overall Change Duration | What is the expected duration of the deployment? | 30 mins
1.4 | Change Type | What is being deployed? (Data/Code, Both)? | etl
1.5 | Matillion Coding Standard | Does your change involve Matillion Code ? If Yes, are there any job varibales in your code that has environmental details (like server IPs, User Passwords, URLs etc)? | YES, but there is not API as environment variable
1.6 | Matillion Coding Standard | If Answered Yes to enviromental details in job variables, have you coordinated with DS Admins already to add the additional endpoint tracked for future change notifications? | YES
1.7 | Matillion Configuration | Do your change have any active Matillion endpoints /Source Systems/Target Systems? | NO
1.8 | Change Description & Justification | Deployment description along with business justification | Alter the table for add the new columns
1.9 | Impact | Does this deployment requires system downtime? | NO
1.9.1 | Admin POC | Are there named resources listed that are executing the deployment? | Yes
1.9.2 | Monitoring POC | Are there named resources listed that are monitoring post-deployment? | Yes
2 | Deployment Rigor
2.1 |  | Is this a first time deployment? | No
2.2 |  | Is the deployment high-risk ? | No
2.3 |  | Will the deployment affect a large group of people ? | NO
2.4 |  | Does the deployment impact a particularily high value area ? | NO
2.5 |  | Will this change have any impact on downstream systems ? | NO
3 | Pre-deployment Testing
3.1 | Perf Test POC | Who was the primary Performance tester? | Amrita
3.2 | Perf Test method | LOAD: How was the load test performed? | validated the new columns added to table
3.3 | Perf Testing vs Prod real load comparison and Test Results | LOAD: What were the load testing results and how close to true production scenarios and traffic volumes where achieved? | validated the table and its as expected
3.4 | Load test reviewer | LOAD: Who approved the load test results? | ram
3.5 | UAT/Functional testing | Functional /UAT : What was tested and what were the results? | na
3.6 | Functional test POC | Who approved functional test results in lower env? | NA
3.7 | UAT/Business signoff POC | UAT: Who outside of IS performed UAT? | NA
4 | Deployment Steps
4.1 |  | Are all deployment tasks listed? | Yes
4.2 |  | Are tasks at a detailed enough level? | Yes
4.3 |  | Is there a single, named owner on each deployment task? | Yes
4.4 |  | Do you have an identified escalation path for each major component of the deployment? | NA
4.5 |  | How will the steps of the deployment process be communicated for "active" (e.g. deployment team) and "passive" (e.g. those who need to stay informed) team members. | Microsoft Teams' chat for Active Members collaborting about the change and/or Email Communication to the Passive Members
5 | Deployment Verification
5.1 |  | Is there a clear "definition of done" for the deployment? | Yes
5.2 |  | Is the criteria for a successfully deployment defined? | NA
5.3 |  | Are named resources within IS listed that are responsible for verifying if the deployment is successful? | NA
5.4 |  | Are named resources outside of IS listed that are responsible for verifying if the deployment is successful? | NA
6 | Monitoring and Alerting
6.1 | Post Deployment monitoring | What related systems require monitoring post-deployment? | SNS is set in the job
6.2 |  | How will all related systems be monitored after deployment to ensure the application is performing as expected? | NA
6.3 |  | What are the Run times/frequency/expected load/any SLAs in production | NA
7 | Rollback
7.1 |  | Is there a detailed, robust rollback plan? | yes, we will rollback our changes
7.2 |  | Has the rollback plan been executed in a non-PROD environment? | NO
8 | Communication
7.1 | Communication POC | Who communicated the deployment details? | SWARNA
7.2 | Notification contact points | Who/what teams need to be aware of this deployment? | DATA_ANALYST
7.3 | Communication Mode | Have all appropriate people and teams been made aware of this deployment? | Yes